## ورقة1
S.No | Description | Status |  | Remarks
1 | Set Busy | Done |  | UI change
2 | Confirmed should change as Pending | Done |  | Name change
3 | Showing How many Pending order, how many accpet order ( Done ) | Done |  | Count for each status
4 | Report Excel Export order | Done |  | export button
5 | Show Order for catergory same like Zyda | Done |  | drag system to change show order of category and products inside
6 | Main Dishes Show order same like Zyda | Done |  | drag system to change show order of category and products inside
7 | Main Dishes Sides like Zyda | Pending |  | clarified
8 | Dishes Available, NA | Done | New | Publishing and unpublishing
9 | User & Permission | Pending | New | in the next phase
10 | Reports to add | Pending |  | will be given by fraderic later
11 | Create Screen Training | Pending |  | add customer not working
12 | In Order Screen name and order number to be add | Done |  | ordernumber should be added
13 | Newset order has to come first | Done |  | order sorting
14 | Create Order has to be send link. | Pending |  | payment link generation
15 | Need side dish option | Done |  | clarified
16 | Need main dish & side dish & add on category wise | Done |  | categorywise list in products
17 | Need default Food preparation time & custom time (hour & Day Also) | Pending |  | add default preparation time in general data
18 | Need Number of person optional | Pending |  | make it text and optional
19 | Main dish & side dish & add-on ,categories make unlimited ,( now only 25 ) | Done | pagination
20 | Make show order auto generated and draw option also | Done |  | drag system to change show order of category and products inside
21 | Side dish and add-on make group and duplicate also | Pending |  | option group
22 | Make block & unblock option in main dish ,categories, side dishes add on also | Done |  | block and unblock, publish and unpublish
23 | Side dish & add-on count make minimum to maximum selection | Done |  | clarified
24 | Main dish delete option not work & search option not work | Done
25 | Side dish option need ( optional price section ) | Done |  | clarified
26 | Main dish -> addon-> delete option not work | Pending
27 | Order Print A4, Thermal | Done
28 | Send Order details to Driver | Done |  | send details to whatsapp
29 | View Map in Order Details | Done |  | google map with lat & lng of shipping address
30 | Need to add delivery charges | Work in Progress |  | current category not showing in update product view
31 | Reports need to have date filter | Work in Progress |  | products and category list only 25
32 | Reports Export option | Work in Progress |  | ads make target items optional
33 | Need order number | Done |  | add price, time to location
34 | Wallet point can add or delete option ( admin have to access ) | Pending
35 | Filter as per categories | Done
36 | Area name in order | Pending
37 | Need Map location | Pending
38 | Delete option not work in addvertisement | Pending
39 | Couldn’t add New addons | Done
40 | Not show all addons in main dish-> addon -> item area | Done